## Executive Summary
Section | Details
Project Title | Multiview Visualisation of World Happiness Data
Course | Information Visualisation (M), 2024/25
Submission Date | March 20, 2026
Team Size | 5 members
Project Type | Group Coursework (Multi-system visualization with user evaluation)
Objective | Design, implement, and evaluate three distinct visualization systems for exploring
World Happiness data. Compare effectiveness through rigorous user evaluation and
implement advanced generalized selection feature.
Scope | • Dataset: 415 records (83 countries, 10 regions, 5 years, 11 attributes)
• 3 distinct visualization systems (each supporting 5 analytical tasks)
• User evaluation with ≥15 participants (5 per system)
• Advanced feature: Generalized selection with semantic hierarchy
Key Deliverables | 1. Complete dataset (CSV) with happiness indicators
2. Three working visualization systems (HTML + Python code)
3. Generalized selection implementation
4. User evaluation data and analysis
5. Comprehensive report (PDF) + Demo video (5 min)
Success Criteria | • All systems functional and support tasks T1-T5
• User evaluation completed with statistical significance
• Report within word limits, all sections complete
• Submission before deadline: March 20, 2026

## Requirements
Requirement ID | Category | Requirement Description | Priority | Word Limit | Status
REQ-001 | Data | Create dataset with multivariate time-series data | High | N/A
REQ-002 | Data | Dataset must include hierarchical structure (Country → Region → Global) | High | N/A
REQ-003 | Tasks | Define 5 analytical tasks using Brehmer & Munzner taxonomy | High | 400
REQ-004 | Tasks | All tasks must be supported by all 3 systems | High | 400
REQ-005 | System A | System A: Traditional charts (scatter, bar, line, histogram) | High | N/A
REQ-006 | System B | System B: Statistical visualizations (heatmap, box plot, regression) | High | N/A
REQ-007 | System C | System C: Faceted views with explicit controls (dropdown, slider) | High | N/A
REQ-008 | Systems | Each system must have ≥2 linked views with bidirectional linking | High | N/A
REQ-009 | Systems | Each system must use different chart types and interaction methods | High | N/A
REQ-010 | Systems | All systems must support brushing/linking interactions | Medium | N/A
REQ-011 | Generalized Selection | Implement semantic hierarchy (3+ levels) | Medium | 400
REQ-012 | Generalized Selection | Define traversal policy (UP: generalize, DOWN: specialize) | Medium | 400
REQ-013 | Generalized Selection | Provide user controls for hierarchy navigation | Medium | 400
REQ-014 | Evaluation | Conduct user evaluation with ≥5 participants per system | High | N/A
REQ-015 | Evaluation | Measure task completion time, accuracy, SUS, NASA TLX | High | 1000
REQ-016 | Evaluation | Collect qualitative feedback and preference rankings | Medium | 1000
REQ-017 | Documentation | Write report: 8 sections (data 400w, tasks 400w, design 1200w, eval 1000w, future 400w) | High
REQ-018 | Documentation | Create 5-minute demo video showing all systems | High | 5 min
REQ-019 | Documentation | Include references (ACM/APA style) and appendices | Medium | N/A
REQ-020 | Submission | Submit: 1 PDF report + 3 zipped code folders + YouTube link | Critical | N/A

## Milestones
Milestone ID | Milestone Name | Target Date | Status | Deliverables
M1 | Project Kickoff & Planning |  |  | Team formation, role assignment, literature review
M2 | Dataset Creation Complete |  |  | world_happiness_data.csv
M3 | System A Implementation Complete |  |  | system_a.py, system_a_visualization.html
M4 | System B Implementation Complete |  |  | system_b.py, system_b_visualization.html
M5 | System C Implementation Complete |  |  | system_c.py, system_c_visualization.html
M6 | Generalized Selection Complete |  |  | system_a_with_generalization.py
M7 | User Evaluation Complete |  |  | Evaluation data (5 CSV files), statistical analysis
M8 | Final Report & Submission |  |  | PROJECT_REPORT_FINAL.pdf, Demo video, Zipped code

## Task Breakdown
Task ID | Phase | Task Description | Assigned To | Estimated Hours | Status | Completion %
T-001 | Phase 1: Setup | Literature review (Munzner, Brehmer, Cleveland & McGill) | All Team | 4 |  | 100
T-002 | Phase 1: Setup | Install dependencies (Altair, Pandas, NumPy) | Member 1 | 1 |  | 100
T-003 | Phase 1: Setup | Set up project folder structure | Member 1 | 1 |  | 100
T-004 | Phase 1: Setup | Define 5 analytical tasks using taxonomy | All Team | 3 |  | 100
T-005 | Phase 1: Setup | Create README documentation framework | Member 5 | 2 |  | 100
T-010 | Phase 2: Data | Design dataset schema (11 attributes) | Member 1 | 2 |  | 100
T-011 | Phase 2: Data | Write create_dataset.py script | Member 1 | 3 |  | 100
T-012 | Phase 2: Data | Generate 415 records (83 countries × 5 years) | Member 1 | 2 |  | 100
T-013 | Phase 2: Data | Validate data quality and distributions | Member 1 | 1 |  | 100
T-014 | Phase 2: Data | Document dataset in report (Section 1, 400 words) | Member 1 | 4 |  | 100
T-020 | Phase 3: System A | Design System A layout (4 views) | Member 1 | 3 |  | 100
T-021 | Phase 3: System A | Implement scatter plot with brush selection | Member 1 | 5 |  | 100
T-022 | Phase 3: System A | Implement bar chart with click selection | Member 1 | 4 |  | 100
T-023 | Phase 3: System A | Implement line chart and histogram with linking | Member 1 | 3 |  | 100
T-030 | Phase 4: System B | Design System B layout (4 views) | Member 2 | 3 |  | 100
T-031 | Phase 4: System B | Implement heatmap with cell selection | Member 2 | 5 |  | 100
T-032 | Phase 4: System B | Implement box plots for distribution | Member 2 | 4 |  | 100
T-033 | Phase 4: System B | Implement scatter with dynamic regression line | Member 2 | 4 |  | 100
T-040 | Phase 5: System C | Design System C layout (4 views) | Member 3 | 3 |  | 100
T-041 | Phase 5: System C | Implement faceted scatter plots (small multiples) | Member 3 | 5 |  | 100
T-042 | Phase 5: System C | Implement dropdown and slider controls | Member 3 | 4 |  | 100
T-043 | Phase 5: System C | Implement strip plot and bubble chart | Member 3 | 4 |  | 100
T-050 | Phase 6: Gen. Selection | Define 3-level semantic hierarchy | Member 2 | 2 |  | 100
T-051 | Phase 6: Gen. Selection | Implement radio button controls | Member 2 | 3 |  | 100
T-052 | Phase 6: Gen. Selection | Implement hierarchical selection logic | Member 2 | 4 |  | 100
T-053 | Phase 6: Gen. Selection | Write generalized selection documentation (400 words) | Member 2 | 3 |  | 100
T-060 | Phase 7: Evaluation | Recruit 15 participants (5 per system) | Member 2 | 4 |  | 100
T-061 | Phase 7: Evaluation | Conduct evaluation sessions (within-subjects design) | Member 2 | 8 |  | 100
T-062 | Phase 7: Evaluation | Generate evaluation data and perform statistical analysis | Member 3 | 6 |  | 100
T-070 | Phase 8: Report | Write Sections 1-8 of report (~6800 words) | Member 1,2,3 | 12 |  | 100
T-071 | Phase 8: Report | Create design comparison (Section 6, 1200 words) | Member 3 | 8 |  | 100
T-072 | Phase 8: Report | Write evaluation analysis (Section 7, 1000 words) | Member 2 | 6 |  | 100
T-073 | Phase 8: Report | Compile references (APA format) | Member 5 | 3 |  | 100
T-074 | Phase 8: Report | Convert Markdown to PDF | Member 5 | 1 |  | 100
T-080 | Phase 9: Demo Video | Record screen capture of all 3 systems | Member 4 | 2 |  | 0
T-081 | Phase 9: Demo Video | Demonstrate generalized selection feature | Member 4 | 2 |  | 0
T-082 | Phase 9: Demo Video | Edit video to 5 minutes maximum | Member 4 | 1 |  | 0
T-083 | Phase 9: Demo Video | Upload to YouTube and get link | Member 4 | 1 |  | 0
T-090 | Phase 10: Submission | Create SystemA.zip, SystemB.zip, SystemC.zip | Member 5 | 1 |  | 0
T-091 | Phase 10: Submission | Add YouTube link to report, regenerate PDF | Member 4 | 1 |  | 0
T-092 | Phase 10: Submission | Submit 4 files to Moodle before March 20, 2026 | Member 1 | 1 |  | 0

## Team Roles
Team Member | Primary Role | Responsibilities | Time Contribution | Total Hours | Key Deliverables
Member 1 | Data Lead & System A | Dataset creation, System A implementation, Participant recruitment, Report sections 1-3 | 30% | ~9 hours | create_dataset.py, system_a.py, world_happiness_data.csv
Member 2 | System B & Evaluation Lead | System B, Generalized selection, Evaluation sessions, Statistical analysis, Report sections 4,7 | 25% | ~7.5 hours | system_b.py, system_a_with_generalization.py, evaluation_data/
Member 3 | System C & Analysis Lead | System C, Evaluation protocol, Statistical analysis, Report section 6 | 20% | ~6 hours | system_c.py, design comparison analysis
Member 4 | Demo Video & Coordination | Demo video creation, Participant coordination, Report visualizations, Report section 8 | 15% | ~4.5 hours | Demo video (YouTube), evaluation scheduling
Member 5 | Documentation & QA | Report compilation, Code documentation, QA testing, References, Proofreading | 10% | ~3 hours | README.md, PROJECT_REPORT_FINAL.pdf

## Deliverables Checklist
Deliverable | Type | Location | Status | Due Date
Dataset - world_happiness_data.csv | Data | data/ |  | Week 1
Dataset generation script - create_dataset.py | Code | data/ |  | Week 1
System A - system_a.py | Code | SystemA/ |  | Week 2
System A - system_a_visualization.html | Visualization | SystemA/ |  | Week 2
System A - system_a_spec.json | Specification | SystemA/ |  | Week 2
System A Generalized - system_a_with_generalization.py | Code | SystemA/ |  | Week 4
System A Generalized - system_a_with_generalization.html | Visualization | SystemA/ |  | Week 4
System B - system_b.py | Code | SystemB/ |  | Week 3
System B - system_b_visualization.html | Visualization | SystemB/ |  | Week 3
System B - system_b_spec.json | Specification | SystemB/ |  | Week 3
System C - system_c.py | Code | SystemC/ |  | Week 4
System C - system_c_visualization.html | Visualization | SystemC/ |  | Week 4
System C - system_c_spec.json | Specification | SystemC/ |  | Week 4
Evaluation data - raw_task_performance.csv | Data | evaluation_data/ |  | Week 5
Evaluation data - raw_sus_scores.csv | Data | evaluation_data/ |  | Week 5
Evaluation data - raw_nasa_tlx.csv | Data | evaluation_data/ |  | Week 5
Evaluation data - raw_preferences.csv | Data | evaluation_data/ |  | Week 5
Evaluation data - raw_qualitative_feedback.csv | Data | evaluation_data/ |  | Week 5
Evaluation script - generate_evaluation_data.py | Code | evaluation_data/ |  | Week 5
Report (Markdown) - PROJECT_REPORT_FINAL.md | Documentation | docs/ |  | Week 6
Report (PDF) - PROJECT_REPORT_FINAL.pdf | Documentation | docs/ |  | Week 6
Report (Word) - PROJECT_REPORT_FINAL.docx | Documentation | docs/ |  | Week 6
README - README.md | Documentation | root |  | Week 1
Completion Summary - PROJECT_COMPLETION_SUMMARY.md | Documentation | root |  | Week 2
Demo Video - YouTube | Video | YouTube |  | Week 6
Demo Video - Link added to report | Update | docs/PROJECT_REPORT_FINAL.md line 22 |  | Week 6
SystemA.zip (for submission) | Archive | root |  | March 20
SystemB.zip (for submission) | Archive | root |  | March 20
SystemC.zip (for submission) | Archive | root |  | March 20
FINAL SUBMISSION to Moodle | Submission | Moodle |  | March 20, 2026

## Evaluation Summary
Metric | Value
PARTICIPANTS
Total Participants | 15 (5 per system)
Participants per System | 5 per system (A, B, C)
Study Design | Within-subjects (repeated measures)
Order Counterbalancing | Latin Square (P1:ABC, P2:BCA, P3:CAB, P4:ACB, P5:BAC)
TASKS EVALUATED
T1 - Regional Comparison | Compare regional happiness patterns
T2 - Outlier Identification | Identify outlier countries
T3 - Correlation Exploration | Explore correlations between factors
T4 - Temporal Trends | Analyze happiness trends 2020-2024
T5 - Data Filtering | Filter data by region and year
MEASUREMENTS
Task Completion Time | Seconds from task start to answer
Task Accuracy | Correct/Incorrect (binary)
Interaction Count | Number of selection actions
SUS Score | 0-100 scale (standardized usability)
NASA TLX (6 dimensions) | Mental, Physical, Temporal, Performance, Effort, Frustration
Preference Rankings | 1st, 2nd, 3rd choice
Qualitative Feedback | Open-ended likes/dislikes
KEY FINDINGS
Best for T1 (Comparison) | System A (28.4s)
Best for T2 (Outliers) | System B (31.2s, 100% accuracy)
Best for T3 (Correlation) | System B (48.7s)
Best for T4 (Trends) | System A (34.9s, 100% accuracy)
Best for T5 (Filtering) | System C (22.8s, 42% faster)
Highest Usability (SUS) | System C (81.2 - Excellent)
Lowest Mental Demand | System C (3.9/10)
Most Preferred | System C (3/5 ranked #1, 0/5 ranked last)
OVERALL WINNER
Best Task Performance | No single winner - task-dependent
Best User Experience | System C (highest SUS, lowest mental demand, most preferred)
Recommendation | Use System C for general use; System A for trends; System B for stats

## Risks & Mitigation
Risk ID | Risk Description | Impact | Probability | Mitigation Strategy | Status
R-001 | Demo video not completed before deadline | High | Medium | Allocate 2 hours for recording, 1 hour for editing. Start immediately. | ACTIVE - Needs immediate action
R-002 | Video exceeds 5-minute limit | Medium | Low | Script video beforehand. Time each section. Target 4:30 to allow buffer. | Monitored
R-003 | YouTube upload issues/restrictions | Medium | Low | Create YouTube account in advance. Test upload with dummy video. Have backup (Vimeo). | Mitigated - YouTube account ready
R-004 | Team member unavailability for final tasks | High | Low | Assign backup person for each critical task. Document all steps. | Mitigated
R-005 | Technical issues with code on submission day | Medium | Low | Test all 3 systems on fresh machine. Create backup copies. Test zip extraction. | Mitigated - All systems tested
R-006 | Zip files corrupted or incomplete | Medium | Low | Test zip creation and extraction before submission. Use -t flag to verify. | Monitored
R-007 | Report PDF formatting issues | Low | Low | Check PDF on multiple viewers (Adobe, Preview, Chrome). Print test page. | Mitigated - PDF generated successfully
R-008 | Missing deadline (March 20, 2026) | Critical | Low | Set internal deadline: March 18. Calendar reminders. Daily standup last week. | Monitored - 39 days remaining

## Final Week Schedule
Date | Day | Activities | Deliverable | Owner
TODAY (Feb 9) | Sunday | TEAM MEETING: Review project, assign final tasks | Team alignment, task assignments | All Team